#### ENC Checklist

#### To-do List: Before Launching the Competition

- Present the idea of organising a WIC to the National/Local Board

- Schedule the project in collaboration with the Board

- Choose the topic of the edition

- Structure the timeline of the entire project

- Contact the various professionals

Specifically:

- Academic Board

- Jury

- Training professionals (if they are not part of the Jury or the Academic Board)

- Actors playing the witnesses (if they are not members of the Organising Committee).

- Jury: Determine the date(s) for the in-person phase

- Work with the Academic Board

- Identify the case for the Competition

- Set deadlines for: first Draft, second draft, and final version of the case

- Set a date to train the actors

- Write the regulations

- Prepare draft emails for contacting the members of the Academic Board and Jury

- Identify the prizes

- Schedule the training sessions (if planned)

- Consider hosting an Opening Conference

- Request accreditation for participation in the Competition (if applicable)

- Coordinate with the other members of the Board, specifically with the the President, the Secretary General, the Treasurer, and the VP in charge of Marketing

- Coordinate and reach out to partners to get financial or in-kind support

- Write the Privacy Policy for the event

- Create the registration form

- Create a budget for the event

- Create the necessary materials and a promotion strategy

- Identify and book the venues for the Competition and, if feasible, a room for the ury and actors for the breaks

#### To-do List: Launching the Competition

- Prepare the email for the launch of the Competition

- Prepare the email for registration confirmation and team code assignment

- Event promotion

- Other tips for effective management and communication with participants:

- Team pairing for individuals who sign up alone and are looking for a partner: establish pairing methods

- Verify membership status of the registered individuals

- Check for conflicts of interest

- Include participants in the mailing list

- Answer any clarification questions

To-do List: The Oral Phase

- Establish the agenda for the Oral Phase

- Have the scoring system and sheets ready for the team evaluation

- Draw the order of the Oral Phase

- Division of tasks within the Board

- Appoint timekeepers

- Actors (if they are part of the Organising Committee)

- Managing participants on-site

- Managing the Jury and partners

- Enjoy the show!

- Announcement of the Winners

#### To-do List: Conclusion of the Competition

- Thank-you emails to supporters

- Issuing participation certificates

- Feedback form